## Sheet1
Seq# | Activity Description | Start Date | End Date | Assigned To | Remarks | Risks
1 | Receive clarifications for all questions | 2020-02-20 | 2020-02-24
2 | Finalize the dataset , clean the data set | 2020-02-20 | 2020-02-25
3 | Validate all the needed software | 2020-02-21 | 2020-02-24
4 | Build the web app | 2020-02-24 | 2020-02-28
5 | Build Hybrid approach for test data | 2020-02-26 | 2020-03-03
7 | Train the data | 2020-03-04 | 2020-03-06
8 | Finalize code and upload to Git | 2020-03-06 | 2020-03-06
9 | User manual , any other expected deliverable | 2020-03-03 | 2020-03-06
6 | Brainstorm on possible outputs to be presented | Everyday during touchbase meeting
10 | Touchbase meetings | Everyday - 4PM to 4:30 PM